## Weekly Report
Week | Week Subtitle | Description
Week 1 Project Planning and Requirements Gathering | Research on Similar Platforms | We will start by looking at other event discovery platforms like Meetup and Eventbrite. We want to see what they do well and where they could improve. For example, in Saudi Arabia, we have platforms like Tadreeb and Mawdoo3. Tadreeb is great for professional development events but can be a bit confusing to navigate. Mawdoo3 has a lot of content but sometimes it's hard to find specific events.
| Defining Scope, Goals, and Objectives | Our project is a smaller version of these big platforms. We'll focus on creating a simple web app. Our main goal is to help users find local events based on their interests. We also want to make networking easier. By the end of this week, we should have a clear idea of what we want to achieve.
| Identifying Target Audience and Their Needs | We need to know who will use our app. Are they students, professionals, or just people looking for fun things to do? We can ask them what kind of events they're interested in and what features they'd like to see in an app. This will help us design something that meets their needs.
| Creating Project Timeline and Assigning Tasks | We'll make a timeline that shows what we need to do each week. We'll also decide who will do what tasks. This will help us stay organized and make sure everything gets done on time.
Week 2 Design and Wireframing | Past Week Achievements | Last week, we did a lot of research and planning. We now have a good understanding of what we want to build and who we're building it for.
| Developing Visual Design | We want the app to be easy to use and visually appealing. We might choose a clean font like Arial and use colors that match our brand, like blue and white. The layout should be simple and easy to navigate.
| Wireframe/Sketch Description | Wireframes are like sketches of our app. They show what each page will look like and where all the buttons and text will go. We'll make wireframes for pages like event discovery, recommendations, and networking. Tools like Sketch or Figma can help us create these. The wireframe for the event discovery page could look something like this:
| Getting Feedback and Revisions | Once we have our wireframes, we'll show them to others to get their thoughts. Maybe they'll suggest changes or point out something we missed. We'll use this feedback to make our wireframes even better.
Week 3 HTML and CSS (Version 1) | Past Week Achievements | In the last week, we created wireframes for our app and got some great feedback. Now we know exactly what our app will look like.
| Coding HTML Structure | It's time to start coding! We'll begin with the event discovery page (index Page). Using the wireframe as a guide, we'll write the HTML code that creates the structure of the page. It might look something like this:
| Implementing CSS Styles | Now that we have the HTML structure, we'll add some style with CSS. We'll choose fonts and colors that match our design. For example, we might use Arial as our font and blue and white as our colors. Here's what the CSS might look like:
Week 4 HTML and CSS (Version 2) | Past Week Achievements | Last week, we coded the HTML structure and added some basic CSS styles. Our event discovery page is starting to take shape!
| Adding More Pages | Now that we have the event discovery page (Index Page), We will add more pages. We could have a recommendations part inside the main page that suggests events based on user preferences. We will a networking page where users can chat with other attendees of the events. Each page will have its own HTML and CSS code. We will also add a feedback page wehre users can write their openions about the events they have attended (We think about adding options like *** stars for evaluation.
| Improving Design | As we add more pages, we can also improve the design. Maybe we want to add some images or change the colors. We can experiment with different designs until we find one that looks great.
| Wireframe/Sketch Description | Wireframes for additional pages like networking, and feedback will be created.
Week 5 Integration and Testing | Past Week Achievements | In the last week, we added more pages to our app and improved the design. It's starting to look really good!
| Integrating Pages | Now that we have all our pages, we need to make sure they work together. When a user clicks on a link, it should take them to the right page. We'll check that all the links and buttons are working correctly.
| Conducting Thorough Testing | Testing is important to make sure our app works well. We'll test it on different devices and browsers to make sure it looks good everywhere. We'll also ask some friends to try it out and give us feedback. If they find any problems, we'll fix them.
Week 6 Additional Features and Enhancements | Past Week Achievements | Last week, we integrated all our pages and did some thorough testing. Our app is almost ready!
| Adding New Features | We can add some extra features to make our app even better. Maybe we want to add a search bar so users can find events quickly. Or a feature that lets users leave feedback after an event. We'll think about what features would be most useful and add them to our app.
| Optimizing Code | As we add new features, we need to make sure our code is still clean and efficient. We might need to make some changes to keep everything running smoothly. We'll also check that our app loads quickly and is easy to use.
Week 7 Documentation and Training | Past Week Achievements | In the last week, we added some great new features and optimized our code. Our app is looking good!
| Creating Documentation | Now that our app is finished, we need to create some documentation. This will help other people understand how to use and maintain the app. We'll write a user manual that explains how to use the app and a technical guide for developers.
| Providing Training Materials | We'll also create some training materials for end-users. This could be videos, tutorials, or written guides that show people how to use the app. We want to make sure everyone can use our app easily.
Week 8 Final Review and Launch | Past Week Achievements | Last week, we created documentation and training materials. We're almost ready to launch!
| Conducting Final Review | Before we launch, we need to do one final review. We'll check that everything is working perfectly and that the app meets all our requirements. We'll also get approval from our stakeholders.
| Launching Web App | Once we've done the final review, it's time to launch! We'll put our app online and start promoting it. We'll monitor how people use the app and listen to their feedback. If they suggest any improvements, we'll make them.

## Code_W3
<!DOCTYPE html>
<html>
<head>
<title>Event Discovery</title>
<link rel="stylesheet" type="text/css" href="style.css">
</head>
<body>
<header>
<h1>Event Discovery</h1>
<nav>
<ul>
<li><a href="#">Home</a></li>
<li><a href="#">Events</a></li>
<li><a href="#">Recommendations</a></li>
<li><a href="#">Networking</a></li>
<li><a href="#">Feedback</a></li>
</ul>
</nav>
</header>
<main>
<section class="event-discovery">
<h2>Discover Events</h2>
<form>
<label for="location">Location:</label>
<input type="text" id="location" name="location">
<label for="interest">Interest:</label>
<select id="interest" name="interest">
<option value="">Select an interest</option>
<option value="technology">Technology</option>
<option value="business">Business</option>
<option value="arts">Arts</option>
</select>
<label for="date">Date:</label>
<input type="date" id="date" name="date">
<button type="submit">Search</button>
</form>
</section>
</main>
<footer>
<p>&copy; 2022 Event Discovery. All rights reserved.</p>
</footer>
</body>
</html>
/* style.css */
body {
font-family: Arial, sans-serif;
margin: 0;
padding: 0;
}
header {
background-color: #f2f2f2;
padding: 20px;
}
header h1 {
margin: 0;
}
nav ul {
list-style-type: none;
margin: 0;
padding: 0;
}
nav li {
display: inline-block;
margin-right: 10px;
}
nav a {
color: #333;
text-decoration: none;
}
.event-discovery {
padding: 20px;
}
.event-discovery form {
margin-bottom: 20px;
}
.event-discovery label {
display: block;
margin-bottom: 5px;
}
.event-discovery input[type="text"],
.event-discovery select,
.event-discovery input[type="date"] {
width: 100%;
padding: 10px;
margin-bottom: 10px;
border: 1px solid #ccc;
border-radius: 4px;
}
.event-discovery button {
background-color: #4CAF50;
color: white;
padding: 10px 20px;
border: none;
border-radius: 4px;
cursor: pointer;
}
footer {
background-color: #f2f2f2;
padding: 20px;
text-align: center;
}

## Code_W4
<!-- Add new pages -->
<section class="recommendations">
<h2>Recommendations</h2>
<!-- List of recommended events goes here -->
</section>
<section class="networking">
<h2>Networking</h2>
<!-- In-app chat or video call options go here -->
</section>
<section class="feedback">
<h2>Feedback</h2>
<!-- Post-event feedback and connection tracking forms go here -->
</section>
.recommendations {
padding: 20px;
}
.networking {
padding: 20px;
}
.feedback {
padding: 20px;
}